## Risk Acceptance Criteria
Risk Acceptance Criteria
| Acceptance Table | Probability
| Impact |  | Rare | Unlikely | Moderate | Likely | Certain
|  | Negligible | 1 | 2 | 3 | 4 | 5
|  | Low | 2 | 4 | 6 | 8 | 10
|  | Medium | 3 | 6 | 9 | 12 | 15
|  | High | 4 | 8 | 12 | 16 | 20
|  | Critical | 5 | 10 | 15 | 20 | 25
Risks within the green zone of the risk matrix are deemed acceptable and within the corporate risk appetite. However, it is still advised to try and avoid, remediate, or transfer the risk if possible
Risks within the amber zone should be mitigated. Alternatively, these risk can be formally accepted by the business or escalated to the senior management team for discussion
Risks within the red zone must be mitigated via appropriate controls. Alternatively, these risk can be formally accepted by the business or escalated to the senior management team for discussion

## Risk Register
Reference ID | Risk Owner | Risk Response | Title | Control Description | Control Title | Control Status | Control Effectiveness | Inherent Impact | Inherent Probability | Inherent Risk | Residual Impact | Residual Probability | Residual Risk | Applicable Framework Controls | Control Justification
R001 | S. G. | Mitigation | Excessive Permissions | Unauthorized users may gain access to ePHI due to excessive user privileges. | Access Controls and Policies |  |  | 5 | 4 | 20 | 5 | 2 | 10 | NIST SP 800-53: AC-6 ISO 27001: A.5.18 HIPAA: 164.312(a)(1) | Access control types such as RBAC will lower the probability that an individual will have the ability to affect the confidentiality, integrity, or availability of data or systems. Policies will standardize the way access is granted within organization environments.
R002 | S. G. | Mitigation | Phishing (Credential Compromise | Workforce members may disclose credentials through phishing attacks due to insufficient training or email protections. | Email Filtering and Employee Training |  |  | 4 | 5 | 20 | 4 | 3 | 12 | NIST SP 800-53: AT-2 ISO 27001: A.6.3 HIPAA: 164.308(a)(5) | Employee training allows employees to identify and report possible phishing attempts, decreasing probability. Email filtering will block possible phishing attempts.
R003 | S. G. | Mitigation | Ransomware Disrupting Clinical Operations | Malware or ransomware may encrypt systems and disrupt patient care. | Adequate Backup Systems and Recurring Testing |  |  | 5 | 4 | 20 | 4 | 4 | 16 | NIST SP 800-53: CP-9, CP-4 ISO 27001: A.8.13 HIPAA: 164.308(a)(7)(ii)(A-B) | Backup systems will allow the organization to continue operation in crisis scenarios. Recurring backup testing is necessary to ensure integrity of backups and business continuity incase of emergencies.
R004 | S. G. | Mitigation | Insufficient Backups | ePHI may be permanently lost due to insufficient backups or untested recovery procedures. | Update Backup Procedures |  |  | 5 | 3 | 15 | 5 | 2 | 10 | NIST SP 800-53: CP-2, CP-9 ISO 27001: A.5.30 HIPAA: 164.308(a)(7) | Ensuring proper procedures for data backups including testing recovery from backups will clarify possible data loss scenarios to be remediated.
R005 | S. G. | Mitigation | Outdated Encryption Standards | Possible breach of ePHI due to deprecated encryption protocols | Update Encryption Protocols and Standards |  |  | 5 | 5 | 25 | 5 | 2 | 10 | NIST SP 800-53: SC-12, SC-13 ISO 27001: A.8.24 HIPAA: 164.312(e)(1) | Updating encryption protocols and standards will protect the confidentiality of ePHI preventing unauthorized decryption.
R006 | S. G. | Transference | Vendor Data Breach | A business associate/third-party may experience a security incident compromising ePHI | Contractual Obligations and Insurance |  |  | 5 | 3 | 15 | 4 | 3 | 12 | NIST SP 800-53: PL-2 ISO 27001: 6.1.3 HIPAA: 164.308(a)(1)(ii)(B) | Cyber liability insurance and appropriate breach language within BAAs will mitigate the impact of a BA security breach. These will lower the financial impact experienced by the company but reputational damage is still likely.
R007 | S. G. | Acceptance | Limited Logging of Low-Risk Systems | Low impact/legacy systems have limited logging capabilities | N/A |  |  | 2 | 2 | 4 | 2 | 2 | 4 |  | Low impact/legacy systems do not contain any confidential information and therefore present a low risk which can be accepted based on company policy
R008 | S. G. | Avoidance | End-of-Life Systems | Unsupported systems can expose the organization to unpatchable vulnerabilities | Retire Outdated Systems |  |  | 3 | 5 | 15 | 0 | 0 | 0 | NIST SP 800-53: SI-1 ISO 27001: A.8.32 HIPAA: 164.308(a)(1)(ii)(A) | End-of-life systems can be decomissioned to avoid unpatchable vulnerabilities where possible.
R009 | S. G. | Mitigation/Transference | Loss of Theft of Mobile Devices | Mobile devices containing regulated information can be lost or stolen | MDM Software and Insurance |  |  | 4 | 4 | 16 | 2 | 4 | 8 | NIST SP 800-53: MP-7 ISO 27001: A.6.7 HIPAA: 164.310(d)(2)(i) | MDM software will allow the organization to remotely wipe company devices of confidential information incase of theft or loss. Insurance will lower the financial impact of replacing lost or stolen equipment.
R010 | S. G. | Mitigation | Insider threat from authorized users | Authorized users may intentionally or unintentionally misuse access to ePHI due to lack of monitoring or role enforcement. | Employee screening, training, and monitoring |  |  | 5 | 3 | 15 | 5 | 2 | 10 | NIST SP 800-53: SP-3, AC-6 ISO 27001: A.6.1 HIPAA: 164.308(a)(3) | Employee screening reduces the likelihood of malicious insiders. Training will reduce accidental misuse of permissions or confidential information. Continous monitoring will detect anamolous activity allowing incident response teams to take approriate action.